## Sheet1
Date | Selenium automation | Research & Development Repository
2017-10-04 | Initial setup project is in process
2017-10-05 | Skeleten of the framework has been developed.Automating RBI page is in process
2017-10-06 | RBI page has been automated & Generic methods are created
2017-10-09 | Calendar rule engine creation and Data is fetching from the Excel sheet is in process
2017-10-10 | From excel sheet the data is fetching into package
2017-10-11 | Calendar rule engine creation is in process.Date picker is automated
2017-10-12 | Calendar rule engine for RBI site have been completed. Calendar rule engine for spot prices site in ongoing
2017-10-13 | Calendar rule engine creation for MCX is ongoing
2017-10-16 | Calendar rule engine creation for MCX and NSE India is ongoing.Datepicker is automated for gold and silver | Settingup Node.Js framework, Desinginign Master screens
2017-10-17 | Calendar rule engine creation for NCDEX and FPI is ongoing | Settingup Node.Js framework, Schema Design for User Master screen
2017-10-19 | Calendar rule engine creation for all the sites has been created | Initial setup is in process with database connection
2017-10-20 | JDBC conection is under process | User Master Add,Edit,Delete,View is completed
2017-10-23 | Basic structure schema has been created | Authentication Security is in process
2017-10-24 | skelton of the databse is created | Authentication Security is ongoing
2017-10-25 | jdbc connection with mysql has been created | Schema structure is created
2017-10-26 | Table is created in the database with schema.Basic Function created through java | User master CRUD operation ran in postman
2017-10-27 | Inserting data from automation is in progress | Working in link to send email for getting password initially
2017-10-30 | Data has been fetched and stored into database for single website | Randam password will send to mail while creating User creation.Change Password,Role,Strategy master screen is completed
2017-10-31 | 2nd link has been automated and data fetched | Working UI design for the User screen
2017-11-01 | Automation on bloomberg site is ongoing | Working UI design for master screens
2017-11-02 | Date format has been changed as per yesterday discussion.Working Automation of remaining sites | Login page validation is completed.Working on Role mapping
2017-11-03 | Automation of fpi site is ongoing | Opportunity screen is completed.Working on Role and strategy mapping
2017-11-06 | Historic gold site has been automated.crude oil in investingcom is in process | Strategy Mapping and Role mapping in screen is done.Working on file Upload
2017-11-07 | Mcx site has been automated | Working on file upload and download for various file format
2017-11-08 | Fetching data from historic gold site | File Upload is done.working on word document in UI
2017-11-09 | Historic gold and Historic silver site has been automated.iron ore has been taken from sgx site and automated | Working on UI to show the word content in screen
2017-11-10 | howe robinson index siteand oanda site has been automated | Working in Strategy Master.when the strategy should be active by representing date
2017-11-13 | All sites has been automated.Working in alignment of data | Adding components based on Office viewer
2017-11-14 | Working in report with framework | Multiple file uploaded using Angular Js.Working on Office Viewer
2017-11-15 | Modifying methods for reusablity | File upload service is done.Working on UI office viewer
2017-11-16 | Collecting data from 1st Nov 2017.Changing hard code into generic code | Working on Office viewer and Comment
2017-11-17 | Nov 1,2 data taken | Working on Office viewer
2017-11-20 | Nov 1 to today data has been fetched | Working on Office viewer and create edit form
2017-11-21 | Testng is in progress | Single file upload is done.working on comments
2017-11-22 | Conversion of TestNG is in progress | Working on comments and multiple file upload
2017-11-23 | Working on automation to TestNG | Working on Multiple File Upload
2017-11-24 | Completed TestNG conversion.working on excel creation | Single file upload comments is done.Working on Multiple File Upload
2017-11-27 | Setting up TestNG using suite file for return purpose | Working on multiple file upload backend service
2017-11-28 | Project has been converted to testng with retry methods | Single File upload UI integeration in Opportunity view page
2017-11-29 | Converting the project as Batch file | Updating strategies,opportunity names and sector type in database
2017-11-30 | Converting the project as Batch file | Worked minor changes in UI and Sector type autopopulate after selecting opportunity name from third table
2017-12-01 | Working on API to fetch data from product_details table | Working on dashboard UI
2017-12-04 | Convertion of batch file is done. | Working on UI: List of opportunities in Dashboard and hyperlink,comments with date and timestamp
2017-12-05 | Task Scheduler for windows is done.Getting value based on product id,from date,to date backend service is done. | List of opportunities in home page ,Comments with date and timestamp is done
2017-12-06 | API Integeration | Screens review changes,Working on strategy multiselect
2017-12-07 | Working on report page chart UI | worked on logo changes and reflected in all screens.Working on strategy multiselect
2017-12-08 | Report chart filter is done..working on UI & all commodities in screen | Working on Mapping strategy multiselect and UI
2017-12-11 | Working on generic UI and backend service for API Integeration | Worked on Dashboard for user.Working on backend service of strategy multimapping
2017-12-12 | Working on Generic UI alignment | Strategy one to many mapping backend service for view and create is done.working on edit method
2017-12-13 | Working on Generic UI & Dashboard page | Working on Strategy master backend service for update method and role mapping in user creation
2017-12-14 | Working on Generic UI & Dashboard page | Worked on strategy master update backend service.Working on role mapping in user creation and new text edit form
2017-12-15 | Dashboard page is completed | Role mapping in user is done.Working on create text edit form
2017-12-18 |  | Working on UI to create text edit form and multiple file view for single opportunity
2017-12-19 |  | Single opportunity multiple file view with comments UI integeration is done.
2017-12-20 |  | Working on create text edit form and multiselect strategy in Opportunity list
2017-12-21 |  | Worked on multi strategy in opportunity master list view page.
2017-12-22 | Working on Generic Report chart | Strategy scheduler for active and inactive timestamp is done.working on text editor form
2017-12-26 | Project testing and working on Generic report chart | Working on Text editor form
2017-12-27 | Testing is done.Working on Generic report chart | Working on Text editor form* | Note*:Using Text editor form simple content word document is created.Facing issue, if word doc is having tables,single word having styles and font color
2017-12-28 | Generic chart Tab UI developed. Started creating web service for chart data | Working on Text editor form*.Working on excel sheet in UI | Note*:Facing issue,if word doc is having styles and color. Table and multiple lines is fixed.
2017-12-29 | Working on integerating web service for chart data in Generic dashboard.Started deploying backend automation code | Working on excel sheet UI and started for Role management
2018-01-02 | Completed UI Integerations.Deployed automation backend code.Need to install Chrome in Linux environment to make Automation code running. | Working on role management* and Word document creation | Note*:Mapping- If role is other than research analyst,ll map with particular research analyst is done.Working on screens based on roles
2018-01-03 | Tried to install Chrome in linux machine.Facing some issues in installing | Working on word document creation* | Note*:Fixed style and color in document creation.File is created with static file name.working on dynamic file name
2018-01-04 | Facing issues in installing Chrome | Working on word document creation* and excel | Note*:Dynamic file name is created. Working on filename.if file is already exists, file name should be changed as copy-file name
2018-01-05 | Facing issues in installing software | Document is created and can view in single opportunity contain list of files.Working on excel sheet
2018-01-08 |  | Working on excel sheet* and UI changes without label | Note*:File upload backend function is done..Working on excel sheet render in view page
2018-01-09 |  | Working on backend logic status update Approved,change request for the file and excel sheet rendering
2018-01-10 |  | Working on backend logic file status (approve,change request)
2018-01-11 |  | Backend logic approve,change request is done.Working on UI integertion
2018-01-12 | Working on Generic UI tabs to Drop down and chart | Working on UI integeration of file status
2018-01-17 | Generic UI tabs drop down is done and generic reprort UI changes also done | File status UI integeration is done.
2018-01-18 | Deployment is in progress | Working on additional file creation backend logic.Working on excel sheet rendering
2018-01-19 | Deployment is in progress | Working on additional file creation backend logic and working on excel sheet rendering
2018-01-22 | Working on home page chart for whole product date ranges | Working on Additional file creation UI integeration
2018-01-23 | Date ranges for whole product is done | Worked on role management and UI changes
2018-01-24 | Flickering in graph is done | Worked on Role management(RA,CIO) based on screens and actions
2018-01-25 |  | Worked on UI changes and audit logs of opportunity status
2018-01-29 |  | Working on status(approve,changerequest) with comments backend logic in opportunity
2018-01-30 |  | Status with comments UI integeration is done.Working on excel sheet rendering
2018-01-31 |  | Working on file upload image backend logic
2018-02-01 |  | Working on database changes for single opportunity with comments and separating file upload based on extension
2018-02-02 | Deployment is in progress and pushing the historical data into database | Working on opportunity with comments and seperated file upload based on extension.Working on UI integeration to show the file in 4 parts
2018-02-05 | Deployment is in progress and pushed historical data except 4 products into database | Working on opportunity comments.sepearting file is done.Working on download for each file
2018-02-06 | Deployment is in progress. | Opportunity with comments is done.working on download option and creating table for opportunity summary data
2018-02-07 | Working on historical data 4 products to store into database.Automation and UI deployment is done | Working on Contact details backend logic.created table for opportunity summary data
2018-02-08 | All product historical data is pushed into database | File Download - Worked on backend service to make file downloadable on clicking file link.
Contact Details - Added columns in the backend for Contact details in Opportunity creation screen. Also modified Opportunity creation service to save the contact details.
2018-02-09 | Dashboard chart - Worked on X and Y axis label based on product and units.Facing issue to avoid scroll in the report chart | Opportunity Summary data - Created backend service classes and working on datatable editable in UI screen
File Download - In file facing issue to get URL path from the project src folders
2018-02-12 | DashBoard chart - Fixed scroll in report page | Opportunity Summary data - Datatable editable for Summary data UI is done.Working on backend webservices for inserting summary table data into database
13-02-2018 | DashBoard chart - In report chart date and units font changed as Bold and graph colour is changed | Opportunity Summary data -Worked on summary data backend service for inserting data into datatable and tested through an API documentation .Working on integeration UI and backend services
Fixes in UI- After Uploading file,the file is updated in file list.Clicking on Approve button the opportunity detail page is updated with status
14-02-2018 | DashBoard chart - In Report chart all the units are shown in graph and checked the commodities name. | Contact Details -Worked on contact details viewed in opportunity view page and working on update contact details
| Fixes - Height and width is fixed without blank space in screen | Opportunity Summary data - Working on integeration UI and backend service(once the data is entered in opportunity the data should be shown in dashboard page)
Working on export units in excel sheet
15-02-2018 | Deployment - All historical data is pushed into server machine.UI also deployed in server machine except Generating chart data in excel sheet | Fixes in UI(Role management) - Research analyst alone can upload files and create document.CIO can view the file and give action like Approve
| Worked on generating excel sheet after selecting commodities and date | File download - Working on download after clicking the file link, the file should be downloaded
Facing issue in download option after generated excel sheet
16-02-2018 | Deployment - Historical data is pushed into server machine.Checked commodities name.After selecting commodity, we can generate units in excel sheet and download option is done
19-02-2018 |  | Opportunity Summary data - From UI the entered values will store into database(Integerating UI and backend logic is done).Working on the stored values should be shown in dashboard page
File download- After clicking the file name the file should be downloaded.Written logic in backend services,Facing issue in integerating web service and angular js
20-02-2018 | Historical data - Removed FII inflows 4 values and inserted Net Investment (Rs Crores) column alone in database.Deployed in server machine FII inflow values | Opportunity Summary data - The values entered through UI is stored in database.Working on integeration, from the database the value shoud be shown in dashboard page
21-02-2018 |  | Opportunity Summary data - In creating opportunity screen itself summary data also can create.After clicking edit option in summary data, it should be editable and can be updated in database is done.Working on dashboard integeration
Contact details -Worked on storing more contact details for single opportunity backend logic is done.working on UI integeration
22-02-2018 |  | Opportunity Summary data - Summary data editable is done in view opportunity screen(referred Research SW excel sheet shared)
Changes in UI - Added scroll bar in opportunity comments,Description dialog box is added for change request and waitlisted,Increased size for displaying file list with scroll bar
Contact details -Facing issue in UI for more contact details
23-02-2018 |  | Contact details - Multiple contact details UI integration is done
Opportunity Summary data - Financial and Non- Financial database is created.Working on Financial summary data service class
26-02-2018 |  | Contact details - Update and view in UI integeration is done
Financial summary data - Worked on Domain and service class.Working on UI integeration to store the data into database
List of companies BSE - Active(3304),Suspended (946),Delisted(2538) downloaded from the bseindia.com
NSE -List of companies from nseindia.com is downloaded